# Phase Transition Monitoring

## 1.1 General Description

The quality of the eventual product results from the quality control of phase transitioning early on during the development processes. To avoid jeopardizing the quality of the final product, an organization should focus on the evaluation of the interim products of requirement analysis, design, test, and implementation.  When life cycles overlap, pre-defining the extent of overlap formally can ensure that all deliverables are completed under a defined overlap strategy.  A formal methodology for determining when it is appropriate to enter subsequent life cycle phases and declaring completion of major milestones can help the organization to better control the phase transition process.

The scope of the phase transition monitoring measurement is by project and product development life-cycle phase.

## Purpose

The phase transition measurements are intended to provide insight into an organization’s transition criteria.  These measurements keep the organization aware of the status of deliverables that may eventually affect product deliverables.

## 1.3 Applicable Product Categories

This measurement applies to all categories listed in the Product Category Definitions table.

## 1.4 Detailed Description - Phase Transition Monitoring Measurement

### Terminology

- Applicable Life Cycle (LC) Phases – Life cycle phases that comprise an organization’s product development process.

- Milestone – The event that marks the successful completion of a Life Cycle phase.

### Counting Rules

- The organization should identify and track the appropriate set of life cycle phases and milestone(s) for their development process.

- Examples of applicable life cycle phases may include Requirements, Design, Development, Test, Pilot, Deployment (release), etc.

- Phase transition monitoring is tracked by project (as applicable to a project).

### Counting Rule Exclusions

None

### Calculations and Formulas

- Total number of planned deliverables for each life cycle phase transition = P(LC)

- Total number of actual deliverables for each life cycle phase transition = A(LC)

- Phase Transition Completeness Percentage: PTC(LC) = (A(LC) ÷ P(LC)) x 100%

### Reporting and Data Format

- Data should be collected and the measurements reviewed periodically by management to determine the need for corrective action.

- Organizations should establish long and short-term measurement performance goals in order to determine process improvement.

- Organizations should determine and apply thresholds to indicate when corrective action is needed.

## 1.5 Sample Charts